## 10-12-15 to 10-23-15
Date | Description of Work | Hours
2015-10-12 | Initial research for Headphone detection and components | 0.5
2015-10-13 | Symbol creation and some schematic capture | 1.5
2015-10-15 | Schematic capture for LiPo circuitry and began P1 schematic capture | 1
2015-10-17 | P1 connections and push buttons made | 1
2015-10-19 | Addition of Piezo buzzer and audio circuitry. | 0.5
2015-10-21 | Control bus and signal wiring. Modified the digital pot choice to fit pin requirements | 1
Total: |  | 5.5

## 10-24-15 to 11-04-15
Date | Description of Work | Hours
2015-10-24 | Started Footprint creation for P1 and other IC's | 1
2015-10-26 | Pad design for most footprints | 1.5
2015-10-30 | Initial Footprint creation completed/ Design Rules Check | 1
2015-11-01 | Connector Placement on PCB. Set up design rules for placement | 0.5
2015-11-03 | Fixed outstanding schematic issues from intial review | 0.75
2015-11-04 | Audio, Power, Charger Circuitry placed on PCB. Updated connector placement | 1.5
Total: |  | 6.25

## 11-05-15 to 11-17-15
Date | Description of Work | Hours
2015-11-05 | Conitnued work on 2 layer board layout | 1
2015-11-10 | Updated Pull up resistors/schematic and schematic review of audio and power circuitry | 0.5
2015-11-14 | Continue work on 2 Layer PCB layout. Identified issues with routing/layout with current configuration (Disccused in meeting) | 0.5
2015-11-17 | Added 4 Layer PCB, Mounting Holes, Rearranged layout to match closer to dev board, routed power section, changed discrete components to 0603. | 3.5
| Total: | 5.5

## 11-18-15 to 12-17-15
Date | Description of Work | Hours
2015-11-22 | Shrunk board from 2"x2.5" to 2" squared | 0.5
2015-11-23 | Moved components to fit new size restraints, rounded corners to follow holes, updated placebound and package keepout areas | 2
2015-12-01 | Completion of component placement on 2" board | 1
2015-12-03 | Routed most of 2" board. Analog and some digital lines left | 1.5
2015-12-05 | Moved piezo buzzer to the top side and to the left. Allows for less clearance inside the case | 0.5
2015-12-10 | Imported sleeptracker logo as mechanical symbol. Added silk screen text. | 0.5
2015-12-14 | Moved components and retrouted to allow for battery to be mounted underneath board | 0.75
2015-12-15 | Complete Footprint resizing/double checked routing. | 0.75
2015-12-16 | Update Silkscreen, Align Assembly notes, Insert Battery location and logo on silkscreen | 1
2015-12-17 | Begin to prepare BOM,Gerber, and Drill Files for first run of PCB. Export DXF for mechanical design. Adjust silkscreen logo. | 1.5
| Total | 10