## 10-12-15 to 10-23-15
Date | Description of Work | Hours
2015-10-12 | Initial research for Headphone detection and components | 0.5
2015-10-13 | Symbol creation and some schematic capture | 1.5
2015-10-15 | Schematic capture for LiPo circuitry and began P1 schematic capture | 1
2015-10-17 | P1 connections and push buttons made | 1
2015-10-19 | Addition of Piezo buzzer and audio circuitry. | 0.5
2015-10-21 | Control bus and signal wiring. Modified the digital pot choice to fit pin requirements | 1
Total: |  | 5.5

## 10-24-15 to 11-04-15
Date | Description of Work | Hours
2015-10-24 | Started Footprint creation for P1 and other IC's | 1
2015-10-26 | Pad design for most footprints | 1.5
2015-10-30 | Initial Footprint creation completed/ Design Rules Check | 1
2015-11-01 | Connector Placement on PCB. Set up design rules for placement | 0.5
2015-11-03 | Fixed outstanding schematic issues from intial review | 0.75
2015-11-04 | Audio, Power, Charger Circuitry placed on PCB. Updated connector placement | 1.5
Total: |  | 6.25

## 11-05-15 to 11-17-15
Date | Description of Work | Hours
2015-11-05 | Conitnued work on 2 layer board layout | 1
2015-11-10 | Updated Pull up resistors/schematic and schematic review of audio and power circuitry | 0.5
2015-11-14 | Continue work on 2 Layer PCB layout. Identified issues with routing/layout with current configuration (Disccused in meeting) | 0.5
2015-11-17 | Added 4 Layer PCB, Mounting Holes, Rearranged layout to match closer to dev board, routed power section, changed discrete components to 0603. | 3.5
| Total: | 5.5

## 11-18-15 to 12-17-15
Date | Description of Work | Hours
2015-11-22 | Shrunk board from 2"x2.5" to 2" squared | 0.5
2015-11-23 | Moved components to fit new size restraints, rounded corners to follow holes, updated placebound and package keepout areas | 2
2015-12-01 | Completion of component placement on 2" board | 1
2015-12-03 | Routed most of 2" board. Analog and some digital lines left | 1.5
2015-12-05 | Moved piezo buzzer to the top side and to the left. Allows for less clearance inside the case | 0.5
2015-12-10 | Imported sleeptracker logo as mechanical symbol. Added silk screen text. | 0.5
2015-12-14 | Moved components and retrouted to allow for battery to be mounted underneath board | 0.75
2015-12-15 | Complete Footprint resizing/double checked routing. | 0.75
2015-12-16 | Update Silkscreen, Align Assembly notes, Insert Battery location and logo on silkscreen | 1
2015-12-17 | Begin to prepare BOM,Gerber, and Drill Files for first run of PCB. Export DXF for mechanical design. Adjust silkscreen logo. | 1.5
| Total | 10

## 12-18-15 to 02-02-16
Date | Description of Work | Hours
2015-12-18 | SleepTrack_V1 Gerber Files generated | 0.5
2015-12-22 | BOM Completed. Digikey Cart updated. | 2
2015-12-22 | Updated Drill File. Fixed Bottom and Top Copper Layers to show Layer Stackup | 1
2016-01-11 | Checked out PCB's. Documented fixes for V2 and electrical checked. | 0.5
2016-01-26 | Partially assembled PCB. Sucessfully attached Photon. | 1
| TOTAL: | 5

## 02-03-16_to_02-28-16
Date | Description of Work | Hours
2016-02-07 | Updated SleepTrack PCB to V2 | 2.5
2016-02-11 | Completed V2 update. 1:1 Artwork Check, verify components, etc. | 1
2016-02-12 | Research small run board houses. Submit Files for manufacture/assembly quote to American Circuits, Circuitology, Screaming Circuits | 1.5
2016-02-23 | Sent Components to elecrow | 0.25
2016-02-28 | Start Layout for remote IMU board | 0.5
| Total: | 5.75

## 02-29-16_to_ 03-22-16
Date | Description of Work | Hours
2016-02-29 | Complete layout of IMU External | 1.5
2016-03-01 | Generate Artwork, BOM,Drill Files for IMU External | 0.5
2016-03-04 | Fix exposed copper issue on 0402 components, generate new Schematic/PCB PDFs | 0.25
2016-03-07 | Fix issue on IMU External where trace is too close to the edge | 0.25
2016-03-15 | Create troublshooting guide to identify issues with first assmebly of prototype | 1
2016-03-20 | Update IMU footprint for Sleeptrack and IMU External board. (Pitch Change from .53mm to.43mm spacing.) Other small changes(tented vias, USB footprint, move Vias, clean up stray/long traces) | 1
| Total: | 4.5